## ActionItems
|  |  | Last Updated: | 2025-05-04 |  |  | Next Zoom (ET): | 2025-05-13 10:00
ACTION ITEM | RANK | PRIORITY | OWNER | ASSIGNED | DUE | DONE | STATUS | NOTES
Prepare launch plan ASE 2.0 | 5 | HIGH | Both | 2025-05-04 | 2025-05-23 | √ | 100%
Prepare operational ASE Website | 5 | HIGH | FC | 2025-05-04 | 2025-05-23 |  | 25% | Install operational template and basic capabilities (mission, services, team, contact)
Prototype GoDaddy / equivalent hosting | 5 | HIGH | LC | 2025-05-04 | 2025-05-23 |  | 25% | Evaluate competitive capabilities of "bare bones" hosting options
B2B Trolling Plan | 4 | MEDIUM | Both | 2025-05-04 | 2025-06-06 |  | Not Started | Review contacts for prospects
Value proposition and pricing strategy | 4 | MEDIUM | Both | 2025-05-04 | 2025-06-06 |  | Not Started | Prepare strawman proposals for discussion
Contact initial prospects | 4 | MEDIUM | LC | 2025-05-04 | 2025-06-06 |  | Not Started | Contact Marj & Jessica - assess collaboration potential
White paper on email deliverability | 2 | LOW | FC | 2025-05-04 | 2025-06-20 |  | Not Started
White paper on DMARC, DKIM, BIMI … | 2 | LOW | FC | 2025-05-04 | 2025-06-20 |  | Not Started
White paper on GDPR & global equivalents | 2 | LOW | LC | 2025-05-04 | 2025-06-20 |  | Not Started
White paper on custom vs. quick website builders | 2 | LOW | LC | 2025-05-04 | 2025-06-20 |  | Not Started

## Lists
Action Status | Check Mark | Priority | Rank
Not Started | √ | HIGH | 500%
On Hold |  | MEDIUM | 400%
Pending |  | LOW | 300%
25% |  |  | 200%
50% |  |  | 0%
75%
100%